## Sprint #5
Sprint 5
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 5 | Sprint 5 - Assignee | Sprint 5 Add Date | Sprint 5 Completion Date | State | Acceptance
1 | Finalize Color Map Feature | Ensure all countries are properly linked to API data to display correct statistics on CO2 emissions. | Development | 4 | Critical | 2025-11-18 | Soham Bhowmick, Lwin Moe | Yes | Soham Bhowmick, Lwin Moe | 2025-11-18 | 2025-11-20 | Ready for refinement
2 | Implement All Data Sources | Integrate all identified datasets so that the dashboard and map features display the correct statistics. | Development | 4 | Critical | 2025-11-18 | Lwin Moe, Chance Kissel | Yes | Lwin Moe, Chance Kissel | 2025-11-18 | 2025-11-20 | Done
3 | Update Sources Page | Listing all data origins so I can verify the reliability of the displayed statistics. | Development | 4 | High | 2025-11-18 | Chance Kissel, Soham Bhowmick | Yes | Chance Kissel, Soham Bhowmick | 2025-11-18 | 2025-11-22 | Done
4 | Finalize Live Data Fetch Feature | Live CO₂ and temperature data automatically so the dashboard shows the latest statistics. | Development | 3 | High | 2025-11-18 | Chance Kissel, Paul Lewis Marcos | Yes | Chance Kissel, Paul Lewis Marcos | 2025-11-18 | 2025-11-22 | Done
5 | Database Update | Database to store only live CO2 and temperature statistics with timestamps to support predictions and historical tracking. | Development | 3 | High | 2025-11-18 | Paul Lewis Marcos, Chance Kissel | Yes | Paul Lewis Marcos, Chance Kissel | 2025-11-18 |  | Ready for refinement
6 | Apply New UI Across Application | Updated user interface so that all pages of the application look polished and professional. | Development | 2 | High | 2025-11-18 | Lwin Moe, Soham Bhowmick | Yes | Lwin Moe, Soham Bhowmick | 2025-11-18 |  | Ready for refinement
7 | Review Main Feature Branches | Merge feature branches safely so that the final version has no conflicts or errors. | Development | 4 | Critical | 2025-11-21 | Lwin Moe, Chance Kissel, Paul Lewis Marcos, Soham Bhowmick | Yes | Lwin Moe, Chance Kissel, Paul Lewis Marcos, Soham Bhowmick | 2025-11-21 |  | Ready for refinement
8 | Prepare Live Demo & Presentation | Plan the demo and presentation, ranking features by importance, so that the live demonstration is smooth and effective. | Presentation | 3 | Critical | 2025-11-23 | Chance Kissel, Lwin Moe, Paul Lewis Marcos, Soham Bhowmick | Yes | Chance Kissel, Lwin Moe, Paul Lewis Marcos, Soham Bhowmick | 2025-11-23 |  | Ready for consideration

## Product Backlog
Sprint 1
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 1 | Sprint 1- Assignee | Sprint 1 Add Date | Sprint 1 Completion Date | Sprint 2 | Sprint 2 - Assignee | Sprint 3 | Sprint 3 - Assignee | Sprint 4 | Sprint 4 - Assignee | Sprint 5 | Sprint 5 - Assignee | State | Estimate (SP) | Acceptance
1 | Main dashboard: CO₂ ↔ Temperature ↔ Glacier mass | As a learner, I want a single dashboard showing CO₂, temperature, and glacier mass together, so I can see how they relate. | Feature | 4 | High | 2025-09-21 | Chance Kissel | No | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick |  |  | Yes | [7 empty] | Ready for implementation | 8 | Dashboard loads with three synchronized views and a short legend; values update when the time window changes.
2 | Navigation menu bar | As a user, I want a clear menu to switch between dashboard, map, and sources pages. | Feature | 1 | High | 2025-09-21 | Lwin Moe | No | Chance Kissel |  |  | Yes | [7 empty] | Ready for implementation | 3 | Menu is visible on every page; keyboard accessible; current section is highlighted.
3 | Color-coded impact map | As a user, I want a world map with color coding so I can see which regions are most affected. | Feature | 1 | Low | 2025-09-21 | Chance Kissel | No |  |  |  | Yes | [7 empty] | Ready for consideration | 8 | Map pans/zooms; color scale and legend present; hovering shows region stats.
4 | Time slider (history + projections) | As a user, I want a time slider to view past data and future scenario curves. | Feature | 1 | High | 2025-09-21 | Soham Bhowmick, Chance Kissel | No | Lwin Moe, Paul Leweis Marcos |  |  | Yes | [7 empty] | Ready for implementation | 5 | Slider adjusts all visible charts; annotated ticks (e.g., decade marks); projection curves labeled.
5 | Unit toggle (°C/°F) | As a user, I want to switch between Celsius and Fahrenheit. | Feature | 1 | High | 2025-09-21 | Lwin Moe | No | Soham Bhowmick |  |  | Yes | [7 empty] | Ready for implementation | 2 | One click toggles units; all labels and tooltips reflect the selected unit.
6 | Source links under each visualization | As a user, I want direct links to data sources so I can verify the data. | Feature/User Request | 1 | Low | 2025-09-21 | Paul Leweis Marcos | No | [11 empty] | Ready for consideration | 2 | Each chart/map shows at least one working source link and last-updated date.
7 | Real-time (or frequent) data updates | Implement data fetchers and caching so visuals reflect the latest available datasets without overloading APIs. | Development activity | 1 | High | 2025-09-21 | Lwin Moe | No | Chance Kissel, Lwin Moe | [10 empty] | Ready for consideration | 8 | Configurable refresh; graceful fallback to cached data; “data as of” timestamp shown.
8 | Automated tests + CI pipeline | Set up unit/UI tests and continuous integration so each change builds and runs tests automatically. | Engineering Improvement | 1 | Low | 2025-09-21 | Chance Kissel | No | [11 empty] | Ready for consideration | 5 | PRs trigger build & tests; failing tests block merge; basic coverage reported.
9 | Usage logging & metrics dashboard | Add client/server logging so we can see feature usage and performance trends over time. | Engineering Improvement | 1 | Low | 2025-09-21 | Soham Bhowmick | No | Soham Bhowmick | [10 empty] | Ready for implementation | 5 | Key events logged; simple internal metrics page with weekly trends.
10 | Accessibility pass (a11y) | Ensure keyboard navigation, sufficient contrast, alt text, and ARIA roles. | Engineering Improvement | 1 | Low | 2025-09-21 | Lwin Moe | No | [11 empty] | Ready for consideration | 5 | Pages pass automated a11y checks; keyboard-only demo verified by team. (
11 | Performance tuning for map & charts | Optimize data transforms and rendering for smooth interactivity on mid-range laptops. | Engineering Improvement | 1 | Low | 2025-09-21 | Paul Leweis Marcos | No | [11 empty] | Ready for consideration | 5 | 60 FPS target on common interactions; initial load <3s on test dataset.
12 | Data validation & error handling | Validate numeric ranges and handle service failures gracefully (offline states, retries). | Development activity | 1 | Low | 2025-09-21 | Chance Kissel | No | [11 empty] | Ready for consideration | 5 | Bad inputs rejected with clear messages; API outage shows non-blocking banner.
13 | Sign in with Google (OAuth 2.0) | As a user, I want to sign in with my Google account using OAuth 2.0 so I don’t have to create a new password and my data stays secure. | Feature/Security | 1 | Low | 2025-09-21 | Paul Leweis Marcos | No | [11 empty] | Ready for consideration | 8 | Clicking Sign in with Google starts OAuth and allows safe cancel/return. The auth code is exchanged server-side (no client secrets). On success, the app creates/looks up the user by verified email and issues a Secure, HttpOnly session cookie; token refresh is handled server-side. Only whitelisted redirect URIs are allowed and the CSRF state is validated. Logout clears the session and revokes refresh tokens. Failures/timeouts show friendly errors and no PII is logged.
14 | Basic security baseline (HTTPS, safe sessions, input checks) | As a user, I want the site to use basic, sensible protections so my login and data aren’t easily exposed. | Feature/Security | 1 | Low | 2025-09-21 | Soham Bhowmick | No | [11 empty] | Ready for consideration | 5 | Site forces HTTPS; session cookies use Secure, HttpOnly, and SameSite. Server validates inputs and shows friendly errors (no stack traces); login has basic rate-limiting. Passwords (if used) are bcrypt/Argon2 hashed; no secrets/tokens in localStorage; logs avoid sensitive data.
15 | Snapshot & share chart/map | As a user, I want to capture a snapshot or get a shareable link of the current view so I can show others the exact data and filters I’m seeing. | Feature | 1 | Nice to Have | 2025-09-21 | Lwin Moe | No | [11 empty] | Ready for consideration | 5 | User can click “Snapshot” to download PNG of current view; “Share” generates a link that reproduces the same filters/time window; works for charts and map.
16 | Causes breakdown on hover | As a learner, I want a hover tooltip that breaks down the main causes for a point/region so I can quickly understand what’s driving the numbers. | Feature | 1 | Nice to Have | 2025-09-21 | Soham Bhowmick | No | [11 empty] | Ready for consideration | 8 | Hovering a point/region shows a small, readable breakdown (top 3 categories + “more”); values and percentages sum correctly; legend matches colors.
17 | “Ways to help / organizations” page | As a user, I want a vetted list of ways to help and trusted orgs so I can take action directly from the site. | Content Feature | 1 | Nice to Have | 2025-09-21 | Paul Leweis Marcos | No | [11 empty] | Ready for consideration | 3 | Page lists vetted orgs with brief descriptions and outbound links; includes disclaimer; mobile-friendly layout; content lives in a CMS/JSON file.
18 | Simple simulation (“what-if” CO₂ & temperature) | As a user, I want to adjust an emissions path (low/medium/high) and a policy start year to see projected global temperature through 2100 side-by-side with a baseline, so I can compare scenarios and explain the trade-offs. | Feature | 1 | Low | 2025-09-21 | Chance Kissel | No | [11 empty] | Ready for consideration | 13 | User can adjust 1–2 sliders (e.g., emissions path) and see updated curves; reset to defaults; guardrails prevent unrealistic inputs; results labeled as “illustrative.”
19 | Sea-level overlay for 2040+ | As a user, I want a sea-level projection layer I can toggle for a given year so I can visualize potential impacts on the map. | Feature | 1 | Low | 2025-09-21 | Soham Bhowmick | No | [11 empty] | Ready for consideration | 13 | Map layer toggle adds semi-transparent sea-level projection; legend explains scenario/year; pan/zoom remains smooth; overlay can be exported in snapshots.
20 | “About us” page | As a visitor, I want an About page with the project’s mission and team so I can understand who built this and how to contact you. | Content Feature | 1 | Nice to Have | 2025-09-21 | Soham Bhowmick | No | [11 empty] | Ready for consideration | 2 | Page shows mission, team, and contact; passes accessibility checks (alt text, headings); appears in site nav and footer.
21 | Usage logging & metrics dashboard | Add client/server logging so we can see feature usage and performance trends over time. | Engineering Improvement | 1 | Low | 2025-09-21 | Soham Bhowmick | Yes | Soham Bhowmick | 2025-09-21 | [9 empty] | Ready for consideration
22 | Use Cases and Use-Case Diagram | Overall use case designs within the system | Development activity | 3 | High | 2025-09-21 | Lwin Moe | Yes | Lwin Moe | 2025-09-21 | 2025-09-25 | [8 empty] | Done
23 | Create Git hub Repo | Create Git hub Repo and add all members | Development activity | 1 | Critical | 2025-09-25 | Soham Bhowmick | Yes | Soham Bhowmick | 2025-09-21 | 2025-09-26 | [8 empty] | Done
24 | High Level Architecural Diagram | Diagram and document overall project architecture | Development activity | 1 | Critical | 2025-09-25 | Chance Kissel | Yes | Chance Kissel | 2025-09-21 | 2025-09-26 | [8 empty] | Done
25 | Sequence UML Diagram | Create Sequnce Diagram | Development activity | 1 | Critical | 2025-09-25 | Paul Lewis Marcos | Yes | Lwin Moe, Paul Leweis Marcos, Chance Kissel | 2025-09-21 | 2025-09-26 | [8 empty] | Done
26 | AI/ML integration to predict models and generate charts | Using data from the past charts and make a smart guess about where the chart is headed in the future. | Feature | 1 | Nice to Have | 2025-10-24 | Lwin Moe | No | Lwin Moe

## Meeting Tracker
Meeting Date | Status | Column 4 | Notes
2025-09-23 | Completed | Chance Kissel, Lwin Moe, Paul Leweis Marcos | We initially discussed who will do what. Mainly about product backlog and what should we do for Sprint #1. We will start on diagram, possilbe coding after this.
2025-09-26 | Completed | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | Completed Architecture Diagram, Use Case Diagrams, and Sequence Diagrams. Discussed Sprint #1 progress and future plans.
2025-09-30 | Completed | Lwin Moe, Chance Kissel, Paul Leweis Marcos, Soham Bhowmick | Sprint #1 Continued
2025-10-07 | Completed | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | Vision Statement
2025-10-10 | Completed | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | Discussion of Sprint #2 progress, Completed documents for Assignment submission. Solved Chance's Github issue. Updated Sprint #2 and Backlog spreadsheet. Assigned tasks
2025-10-24 | Completed | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | Discussion of Sprint #3 progress, Discussed potential machine learning model to predict future data, discussed where to host website
2025-10-30 | Completed | Lwin Moe, Chance Kissel | Issue with live data integration

## Tasks Tracker
Assignee | Deadline | Status | Notes

## Sprint #1
Sprint 1
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 1 | Sprint 1- Assignee | Sprint 1 Add Date | Sprint 1 Completion Date | State | Acceptance
1 | Main dashboard: CO₂ ↔ Temperature ↔ Glacier mass | As a learner, I want a single dashboard showing CO₂, temperature, and glacier mass together, so I can see how they relate. | Feature | 4 | High | 2025-09-21 | Chance Kissel | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-09-21 |  | Ready for implementation | Dashboard loads with three synchronized views and a short legend; values update when the time window changes.
2 | Navigation menu bar | As a user, I want a clear menu to switch between dashboard, map, and sources pages. | Feature | 3 | High | 2025-09-21 | Lwin Moe | Yes | Chance Kissel | 2025-09-21 |  | Ready for implementation | Menu is visible on every page; keyboard accessible; current section is highlighted.
3 | Time slider (history + projections) | As a user, I want a time slider to view past data and future scenario curves. | Feature | 3 | High | 2025-09-21 | Soham Bhowmick, Chance Kissel | Yes | Lwin Moe, Paul Leweis Marcos | 2025-09-21 |  | Ready for implementation | Slider adjusts all visible charts; annotated ticks (e.g., decade marks); projection curves labeled.
4 | Unit toggle (°C/°F) | As a user, I want to switch between Celsius and Fahrenheit. | Feature | 1 | High | 2025-09-21 | Lwin Moe | Yes | Soham Bhowmick | 2025-09-21 |  | Ready for implementation | One click toggles units; all labels and tooltips reflect the selected unit.
5 | Real-time (or frequent) data updates | Implement data fetchers and caching so visuals reflect the latest available datasets without overloading APIs. | Development activity | 4 | High | 2025-09-21 | Lwin Moe | Yes | Chance Kissel, Lwin Moe |  |  | Ready for consideration | Configurable refresh; graceful fallback to cached data; “data as of” timestamp shown.
6 | Usage logging & metrics dashboard | Add client/server logging so we can see feature usage and performance trends over time. | Engineering Improvement | 1 | Low | 2025-09-21 | Soham Bhowmick | Yes | Soham Bhowmick | 2025-09-21 |  | Ready for implementation | Key events logged; simple internal metrics page with weekly trends.
7 | Use Cases and Use-Case Diagram | Overall use case designs within the system | Development activity | 3 | High | 2025-09-21 | Lwin Moe | Yes | Lwin Moe | 2025-09-21 | 2025-09-25 | Done | Ready to submit
8 | Create Git hub Repo | Create Git hub Repo and add all members | Development activity | 1 | Critical | 2025-09-25 | Soham Bhowmick | Yes | Soham Bhowmick | 2025-09-21 | 2025-09-26 | Done | Add all members
9 | High Level Architecural Diagram | Diagram and document overall project architecture | Development activity | 1 | Critical | 2025-09-25 | Chance Kissel | Yes | Chance Kissel | 2025-09-21 | 2025-09-26 | Done | Ready to submit
10 | Sequence UML Diagram | Create Sequnce Diagram | Development activity | 1 | Critical | 2025-09-25 | Paul Lewis Marcos | Yes | Lwin Moe, Paul Leweis Marcos, Chance Kissel | 2025-09-21 | 2025-09-26 | Done | Ready to submit

## Sprint #2
Sprint 2
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 2 | Sprint 2 - Assignee | Sprint 2 Add Date | Sprint 2 Completion Date | State | Acceptance
1 | Ensure Github is working properly across team | All team members should be able to pull and push accordingly. | Feature | 4 | High | 2025-10-06 | Chance Kissel, Lwin Moe | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-10-06 | 2025-10-10 | Done | Everyone is connected.
2 | Browsing Open-Source Templates | We need to find a good open-source templates that aligns with our requirements | Feature | 4 | Critical | 2025-10-06 | Lwin Moe | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos | 2025-10-07 | 2025-10-10 | Done
3 | Usage logging & metrics dashboard | Add client/server logging so we can see feature usage and performance trends over time. | Engineering Improvement | 3 | High | 2025-09-21 | Soham Bhowmick | Yes | Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-09-21 | 2025-10-10 | Ready for consideration
4 | Finding open-source backend data | Research and idenify reliable open-source datasets | Development | 4 | Critical | 2025-10-10 | Lwin Moe, Soham Bhowmick | Yes | Chance Kissel, Lwin Moe | 2025-10-10 | 2025-10-10 | Ready for refinement
5 | Integrating backend data | Connect and format datasets to be usable by the dashboard | Development | 4 | Critical | 2025-10-10 | Lwin Moe, Paul Lewis Marcos | Yes | Lwin Moe, Chance Kissel, Paul Leweis Marcos, Soham Bhowmick | 2025-10-10 | 2025-10-10 | Ready for refinement
6 | Design and implement main dashboard layout | Create overall user interface of dashboard | Development | 4 | High | 2025-10-10 | Lwin Moe, Chance Kissel | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-10-10 | 2025-10-10 | Done
7 | Connect dashboard componenets to backend data | Linking frontend with backend | Development | 2 | Medium | 2025-10-10 | Paul Lewis Marcos | Yes | Lwin Moe, Paul Leweis Marcos | 2025-10-10 | 2025-10-10 | Ready for refinement
8 | Develop CO2, Temperature, and glacier data visualization chart | Build interactive and clear charts | Development | 1 | Low | 2025-10-10 | Chance Kissel | Yes | Chance Kissel, Soham Bhowmick | 2025-10-10 | 2025-10-10 | Ready for consideration
8 | Navigation menu bar | As a user, I want a clear menu to switch between dashboard, map, and sources pages. | Feature | 3 | High | 2025-09-21 | Lwin Moe | Yes | Chance Kissel | 2025-09-21 | 2025-10-10 | Done
9 | Time slider (history + projections) | As a user, I want a time slider to view past data and future scenario curves. | Feature | 3 | High | 2025-09-21 | Soham Bhowmick, Chance Kissel | Yes | Lwin Moe, Paul Leweis Marcos | 2025-09-21 | 2025-10-10 | Ready for consideration
10 | Unit toggle (°C/°F) | As a user, I want to switch between Celsius and Fahrenheit. | Feature | 1 | High | 2025-09-21 | Lwin Moe | Yes | Soham Bhowmick | 2025-09-21 | 2025-10-10 | Done
11 | Real-time (or frequent) data updates | Implement data fetchers and caching so visuals reflect the latest available datasets without overloading APIs. | Development activity | 4 | High | 2025-09-21 | Lwin Moe | Yes | Chance Kissel, Lwin Moe | 2025-10-13 | 2025-10-17 | Ready for consideration

## Sprint #3
Sprint 3
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 3 | Sprint 3 - Assignee | Sprint 3 Add Date | Sprint 3 Completion Date | State | Acceptance
1 | Finding open-source backend data | Research and idenify reliable open-source datasets | Development | 4 | Critical | 2025-10-21 | Lwin Moe, Soham Bhowmick | Yes | Chance Kissel, Lwin Moe | 2025-10-24 |  | Ready for consideration
2 | Integrating backend data | Connect and format datasets to be usable by the dashboard | Development | 4 | Critical | 2025-10-21 | Lwin Moe, Paul Lewis Marcos | Yes | Lwin Moe, Chance Kissel, Paul Leweis Marcos, Soham Bhowmick | 2025-10-24 |  | Ready for consideration
3 | Improve main dashboard layout | Create overall user interface of dashboard | Development | 4 | High | 2025-10-21 | Lwin Moe, Chance Kissel, Soham Bhowmick, Paul Lewis Marcos | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-10-24 |  | Ready for consideration
4 | Connect dashboard componenets to backend data | Linking frontend with backend | Development | 2 | Medium | 2025-10-21 | Paul Lewis Marcos | Yes | Lwin Moe, Paul Leweis Marcos | 2025-10-24 |  | Ready for consideration
5 | Refine CO2, Temperature, and glacier data visualization chart | Build interactive and clear charts | Development | 1 | Low | 2025-10-21 | Chance Kissel | Yes | Chance Kissel, Soham Bhowmick | 2025-10-24 |  | Ready for implementation
6 | Navigation menu bar | As a user, I want a clear menu to switch between dashboard, map, and sources pages. | Feature | 3 | High | 2025-10-21 | Lwin Moe | Yes | Chance Kissel | 2025-10-24 |  | Ready for refinement
7 | Time slider (history + projections) | As a user, I want a time slider to view past data and future scenario curves. | Feature | 3 | High | 2025-10-21 | Soham Bhowmick, Chance Kissel | Yes | Lwin Moe, Paul Leweis Marcos | 2025-10-24 |  | Ready for consideration
8 | Unit toggle (°C/°F) | As a user, I want to switch between Celsius and Fahrenheit. | Feature | 1 | High | 2025-10-21 | Paul Lewis Marcos, Soham Bhowmick | Yes | Soham Bhowmick | 2025-10-21 | 2025-10-23 | Done
9 | Real-time (or frequent) live data updates | Implement data fetchers and caching so visuals reflect the latest available datasets without overloading APIs. | Development activity | 4 | High | 2025-10-21 | Lwin Moe, Chance Kissel | Yes | Chance Kissel, Lwin Moe | 2025-10-24 |  | Ready for consideration
10 | Toggle to change between Dark and Light Theme | Switching between dark mode and light mode theme for the system | Feature | 1 | Nice to Have | 2025-10-20 | Soham Bhowmick | Yes | Soham Bhowmick | 2025-10-21 | 2025-10-24 | Done

## Sprint #4
Sprint 4
ID | Task | Description | Type | Priorirty | Importance | Date Added | Added By | Sprint 4 | Sprint 4 - Assignee | Sprint 4 Add Date | Sprint 4 Completion Date | State | Acceptance
1 | Connect dashboard componenets to backend data | Linking frontend with backend | Development | 2 | Medium | 2025-10-21 | Paul Lewis Marcos | Yes | Lwin Moe, Paul Leweis Marcos | 2025-10-31 |  | Ready for refinement
2 | Integrating backend data | Connect and format datasets to be usable by the dashboard | Development | 4 | Critical | 2025-10-21 | Lwin Moe, Paul Lewis Marcos | Yes | Lwin Moe, Chance Kissel, Paul Leweis Marcos, Soham Bhowmick | 2025-10-31 |  | Ready for implementation
3 | Finding open-source backend data | Research and idenify reliable open-source datasets | Development | 4 | Critical | 2025-10-28 | Lwin Moe, Soham Bhowmick | Yes | Chance Kissel, Lwin Moe | 2025-10-31 |  | Ready for implementation
4 | Improve main dashboard layout | Create overall user interface of dashboard | Development | 4 | High | 2025-10-21 | Lwin Moe, Chance Kissel, Soham Bhowmick, Paul Lewis Marcos | Yes | Chance Kissel, Lwin Moe, Paul Leweis Marcos, Soham Bhowmick | 2025-10-31 |  | Ready for consideration
7 | Time slider (history + projections) | As a user, I want a time slider to view past data and future scenario curves. | Feature | 3 | High | 2025-10-21 | Soham Bhowmick, Chance Kissel | Yes | Lwin Moe, Paul Leweis Marcos | 2025-10-24 |  | Ready for consideration